## Main
AMRUT - KWA - STATUS AS ON 14.02.2021
No: of Projects | No: of packages | SAAP YEAR | AMRUT Project ID in MoHUA site | NAME OF WORK | AS DATE | AS AMOUNT (in Crores) | PRESENT STATUS | PRESENT PROGRESS (%) | PROPOSED TIME OF COMPLETION | ISSUES | Expenditure (in crores)
TRIVANDRUM
PROJECT DIVISION, TRIVANDRUM
WATER SUPPLY SECTOR
1 | 1 | 15-16-17 | KER-THI-001 & KER-THI-017 | Improvement of water supply scheme - Construction of 75mld Water Treatment Plant at Aruvikkara | 23/2/2017 | 70 | The line is charged successfully and the plant is fully ready for commissioining. | 99% | 2021-02-11 |  | 53.46
2 | 2 | 16-17 | KER-THI-018 | Construction of smart office in Thiruvananthapuram - Kowdiar, Pongmoodu, Vellayambalam 2016-17 | 15/08/2017 | 1.75 | Pongumoodu office - Work completed (Inaugurated on 17/8/20.) Vellayambalam office - Work completed (Inaugurated on 7/8/20), Kowdiar office - Work is going on, upto floorbeam & flor slab. | 73% | 2021-05-28 | Only oral direction received from Corporation for starting Kowdiar office work. | 0.25617
3 |  | 16-17 |  | Supplying and Installation of smart meters | 27/9/2017 | 2.29 | Work split in to two packages |  |  |  | 0.008
| 3 | 16-17 | KER-THI-290 | Supplying and Installation of smart meters - Phase I |  | 1.27 | Meters supplied. Out of 390 meters 152 meters installed. | 36% | 2021-04-28
| 4 | 16-17 | KER-THI-291 | Supplying and Installation of smart meters - Phase II |  | 1.02 | Agreement executed on 6.3.2019 Interlinking software work was entrusted with Kerala Start-up Mission & they failed to come up to the expectation. The supply & installation of smart meters were awarded to a different agency & they could not start work since the software development got delayed. Hence, Contractor have expressed their unwillingness to continue with the work & requested to relieve them. Work retendered on 03/02/20221. Due to single offer, extended till 18/02/2021
4 | 5 | 17-18 | KER-THI-031 | Installation of Flow meters | 2018-01-01 | 7.5 | Work inclueds installing flow meters of size 90mm to 1200mm in trunk mains and inlet/outlet of service reservoirs in TMC (53 Nos), Level Transmitter (20 Nos). Work is in progress. | 46% | 2021-07-31 |  | 1.36
|  |  |  | TOTAL - WATER SUPPLY |  | 81.54 |  |  |  |  | 55.0842
SEWERAGE SECTOR
1 | 1 | 15-16 | KER-THI-005 & KER-THI-021 | Decentralized 5MLD sewerage treatment plant (STP) at Medical College including water recycling plant and reuse | 23/02/2017 | 19.16 | Terminal manhole construction ongoing. Intake well mechanical erection done. Blower room erection done. Mbbr & equalization tank & tube settler civil work including plastering completed. Hydraulic testing done. Mechanical components erection is ongoing. Recycling lines pipe line work commenced. ETP Construction at Medical College ongoing. ETP @SAT Campus started & ongoing. | 73% | 2021-03-03 |  | 7.994
2 | 2 | 15-16 | KER-THI-006 | Construction of sewerage pump house at Edathara in Thiruvananthapuram Corporation | 23/2/2017 16/9/2020 (Revised A.S) | 8.21 | Design approved by WASCON. Forest clearance received and trees have been cut down. Land Acquisition needed for laying gravity main through Amayizhanjan thodu. Site clearance has been done. Joint Inspection has been done with Kadakampally Village officer for determining the face value of the land to be acquired for laying the gravity connection pipe from grit chamber to manhole in the Poonthi road.. |  | 2021-12-31 |  | 0.16
3 | 3 | 15-16 | KER-THI-007 | Supplying and Laying 600mm dia DI Pumping main from Pump at Edathara to STP at Muttathara in Thiruvananthapuram Corporation. | 23/2/2017 | 17.29 | Out of 8700metre, 47% laying completed. Tested Pipe arrived at site for balance laying. Contractor's bill pending with Trivandrum Corporation. | 45% | 2021-03-03 | NHAI permission pending 600 mm DI Pipe 45 m at Lords hospital - Through HDD method (Depth - 2 to 8m below the existing Ground level) Contractor's bill pending with Trivandrum Corporation. Near to railway bridge near Chackai, the Irrigation Authorities raised objection to lay the pipes beside their retaining wall and directed to hold and asked for formal approval from inland navigation.. | 9.35
4 |  | 16-17 |  | Laying transmission main and sewer networks in Block L (Edathara) -Collection and Conveyance system | 2/11/2017 16/9/2020 (Revised A.S) | 29.94 | Work split into 6 packages. |  |  |  | 5.229
| 4 | 16-17 | KER-THI-067 | (a) Laying trunk main from Stilling chamber at Pulayanarkotta to MH 10 of Pumping station at Edathara (Part 1) |  | 15.58 | 700 mm RCC NP3 pipe -300 m completed out of 304.00m 800 mm RCC NP3 pipe - 425m completed out of 1120.00m 1000mm RCC NP3 pipe - 250 m completed out of 1690.0 m Construction of MH 9 nos completed out of 110 nos Stilling chamber-completed | 21% | 2021-05-31 | KRFB road cutting nod at Kumarapuram Poonthi road yet to get. Road restoration amount paid to KRFB.sanction to be obtained.
| 5 | 16-17 | KER-THI-071 | Supplying and laying sewer line through Pettah Venpalavattom road, Greenpark road and side of Amayizhanjan thodu and to MH 7 Edathara zone500mm (RCC pipe-1530m) - pakage 2 |  | 2.94 | Tender invited with opening on 27.10.2020. No offer received in the first tender call. Retendered after election code o f conduct. Opening was on 13.1.2021. No offer received. Tender Notice issued on 24/01/2021, with opened on 15/2/2021. No offer was received. |  |  | Rupees 2.72 Cr. was deposited to the Irrigation department for the construction of side wall in Amayizhanjanthodu. On 13.01.2020, EE, Irrigation has informed that theoriginal proposal was for 900m length & needed revision. Amount is not sufficient for the work.
| 6 | 16-17 | KER-THI-072 | Laying transmission main and sewer network in block L Edathara- collection and conveyance system- Supply and laying trunk main from stilling chamber at Udhaya Garden to MH 89- pakage 3 |  | 1.96 | 1) 500mm RCC NP3 pipe - 460m completed out of 474 m 2) 600mm RCC NP3 pipe - 80m completed out of 620.00 m 3) construction of MH - 18 nos completed out of 54 nos Construction of stilling chamber - sidewall completed | 47% | 2021-03-03
| 7 | 16-17 | KER-THI-073 | Sewer network from Pettah Arasumoode junction to MH-7 Edathara pumping station package 4 |  | 4.93 | First Tender - Two offer received. Due to high quoted rate in the first tender call. Tender cancelled First Tender(after estimate revision) Two offer received. Due to high quoted rate in the first tender call.tender cancelled. First re-tender . Two offer received.lowest offer (31.50 % above TPAC). openend on 30.7.2020. Under scrutiny in H.O KWA Board held on 23.12.2020 approved the tender, subject to approval of SHPSC, AMRUT. To be placed in the next SHPSC. |  |  | Tender excess - Additional amount shall be borne by UB - Resolution from Corporation pending.
| 8 | 16-17 | KER-THI-074 | Laying sewer network in L block (Edathara) from MH 110 to MH 150 (package 5) |  | 1.76 | First Tender -Two offer received.Due to high quoted rate in the first tender call tender cancelled First Tender(After revision) - Two offer. Due to high quoted rate in the first tender call. Tender cancelled First re-tender -tender openend on 24.7.2020 .Single offer offer received.43% above. Tender under scrutiny. KWA Board held on 23.12.2020 approved the tender, subject to approval of SHPSC, AMRUT. To be placed in the next SHPSC. |  |  | Tender excess - Additional amount shall be borne by UB - Resolution from Corporation pending.
| 9 | 16-17 | KER-THI-292 | AMRUT-Laying transmission main and sewer network in Block L Edathara-collection and conveyance system- Laying Sewer network by HDD method from MH 10 towards KIIMS Hospital (Package 6) |  | 2.77 | Tender openend on 30.7.2020. Two offers received.33.95 % and 24.05 % above. KWA Board held on 23.12.2020 approved the tender, subject to approval of SHPSC, AMRUT. To be placed in the next SHPSC. |  |  | Tender excess - Additional amount shall be borne by UB - Resolution from Corporation pending.
5 | 10 | 17-18 | KER-THI-034 | Supplying and erection of pumpsets, transformer and electrical accessories in the Block- L, Edathara Pumping Station | 30/3/2019 | 4 | First Tender -No offer First re-tender(RT1)- No offer Second re-tender (RT2)- no offer Third re-tender (RT3-) -No offer Fourth re-tender (RT4) -Single offer received. Tender opened on 6.8.2020 (31.99 % above TPAC). Tender committe met on 4/11/2020 in H.O decided to cancel the tender. Retendered with opening date 27.01.2021. One offer received. |  |  |  | 0.02
6 | 11 | 17-18 | KER-THI-035 | Construction of Pumping station at Akkulam (Block K) | 2017-02-11 | 4 | 1) 2 nos of well of dia 6.5 m ,well 1=13.8 m completed, well 2=15.0 m completed, RCC plugging completed 2) Grit chamber of size 12.7x4.9 =not started 3)Construction of pump house compound wall = not started 4)construction of 4 nos of MH=not started | 22% | 2021-05-31
7 | 12 | 17-18 | KER-THI-036 | Supplying and laying 450mm DI K9 pumping main for a length of 1800m(Block K - Akkulam pumping station on Pulayanarkotta stilling chamber) | 2017-02-11 | 2.28 | Work completed. | 100% | Completed |  | 2.1669
8 | 13 | 17-18 | KER-THI-037 | Supplying and laying Transmission main in Block K (Akkulam) to connect stilling chamber at Bypass junction to pumping station at Akkulam collection and conveyance system | 2017-02-11 | 7 | 630 mm HDPE - 728 M completed out of 971.00 m Construction of MH, outof 54 nos, 9 completed & 2 in progress | 37% | 2021-03-30 | Since 24.4.2018 KWA has requested NHAI to accord road cutting permission 600 mm HDPE 40 m near Kuzhivila bridge - Through HDD method (Depth - 2 to 8m below the existing Ground level) Online application submitted by KWA. KWA has submitted agreement and undertaking as per the direction of NHAI on 5.10.2020 and sanction is awaiting. Project Director office , NHAI informed that bank guarantee forwarded to Regional office for further process . | 1.268
9 | 14 | 17-18 | KER-THI-035 | Supplying and erection of pumpsets, transformer and electrical accessories in the Akkulam Pumping Station (Block K) | 2017-02-11 | 1.8 | Tender opened on 5.10.2020. Single offer received 45% above TPAC . Tender placed in the tender committee held on 30/11/2020. Directed SE, Trivandrum to collect market rate and compare with quoted rate so as to place in the next tender committee. TC which met on 20.12.20 directed to retender the work. To be retendered.
10 | 15 | 17-18 | KER-THI-039 | Construction of Pumping station at Karimanal (Block J) | 2017-02-11 | 4 | Roof slab concrete work completed. Well no.1&2 dewatering, soil removing ,soil excavation works in progress. | 52% | 2021-05-03 | Funds to be received from Trivandrum Corporation for the last submitted bill. | 0.5422
11 | 16 | 17-18 | KER-THI-040 | Supplying and laying 350mm DI K9 pumping main (Karimanal pump station to stilling chamber at Bypass junction)(Block J) | 2017-02-11 | 1.3 | Work Completed | 100% | Completed |  | 0.32
12 |  | 17-18 |  | Laying Transmission main and sewer networks in Block J (Karimanal) - Collection & Conveyance system | 2017-02-11 | 15.02 | Work split in to 3 components |  |  |  | 0.6028
| 17 | 17-18 | KER-THI-297 | Trunk main to Karimanal |  | 12.73 | 8 nos of man hole works partially completed,5 nos of man hole works is going to complete, HDPE pipe line works in progress | 19% | 2021-08-31 | NHAI to accord road cutting permission 600 mm HDPE 50 m near Thampuranmukku junction - Through HDD method (Depth - 2 to 8m below the existing Ground level) Online application submitted by KWA. KWA has submitted agreement and undertaking as per the direction of NHAI on 5.10.2020 and sanction is awaiting.Project Director office , NHAI informed that bank guarantee forwarded to Regional office for further process .
| 18 | 17-18 | KER-THI-298 | Sewer network from Bypass Jn (Kuzhivila) to MH3 of trunk main from Arasumoodu to Karimanal Pumping station |  | 1.59 | First Tender - Single offer received. no additonal offer received. Tender cancelled. First re-tender(RT1) -Single offer received. Due to high quote rate tender canelled (90% above) Second re-tender (RT2) No offer received. Hence cancelled. third re-tender (RT3) -No offer received. Hence cancelled. forth re-tender (RT4) - No offer received. Hence cancelled. fifth re-tender (RT5) - Single offer received. Single offer received 49 % above TPAC . Tender placed in the tender committee held on 30/11/2020. Decided to retender the work. To be retendered
| 19 | 17-18 | KER-THI-299 | Inter connection sewer networks from trunk main man holes of both sides of the road from Arasumoodu |  | 0.7 | Work in progress. 48 nos of small connection man hole works done. | 12% | 2021-08-30
13 |  | 17-18 |  | Providing Sewer trunk from Kazhakoottam area to Pumping station of I Block through the bank of Thettiyar Thodu - Collection & Conveyance system and pumping station, pumps and electrical installation, Pumping mains (Block I) | 2/11/2017 16/9/2020 (Revised A.S) | 10.56 | Work split into 4 packages. |  |  |  | 0.92
| 20 | 17-18 | KER-THI-207 | (A) 350mm DI K9 PM from well at Kulathoor to stilling chamber at Arasumoode |  | 1.06 | Work Completed | 100% | Completed
| 21 | 17-18 | KER-THI-209 | (B)Well at Kulathoor |  | 3 | First Tender(After revision Pumping station)- No offer First Tender (After clubbing the Pumping station and Pump & elelctrical installation) No offer First re-tender -Two offeres were received. As the amount quoted is too high the tender cancelled. Second re-tender . openend on 10.8.2020. single offer .40 % above TPAC. Tender placed in the tender committee held on 30/11/2020 and 20/12/2020. Placed in the KWA Board held on 28/01/2021. KWA Board held on 28.01.2021 approved the tender, subject to approval of SHPSC, AMRUT. To be placed in the next SHPSC. |  |  | Tender excess - Additional amount shall be borne by UB - Resolution from Corporation pending.
| 22 | 17-18 | KER-THI-211 | (C) Sewer transmission main to Kulathoor |  | 4.8 | Work order issued on 27.5.2020. Agreement not executed.Final notice issued to the firm on 10.10.2020 for executing the agreement on or before 23.10.2020. The tender has been cancelled. Since GST was not included in the estimate, the estimate has to be revised and revised T.S to be issued. To be retendered. |  |  | Permission from Technopark pending
| 23 | 17-18 |  | (D) Supplying and Erection of Pumpsets , transformer and electrical accessories in the Kulathur Pumping Station |  | 1.7 | Status same of package B (Combined tender for package B & D)
14 | 24 | 17-18 | KER-THI-043 | Supplying and erection of pumpsets , transformer and electrical accessories in the Karimanal Pumping Station(BlockJ) | 2017-02-11 | 1.5 | First tender - No offer, cancelled. First Tender (after estimate revised with GST component ) - No offer First re-tender(RT1) -. No offer Second re-tender (RT2) Single offer received 64 % above TPAC. On verification, peak flow of 0.29 m3/s cannot be met by the proposed pumpsets. HenceCE (SR) directed SE, Trivandrum to cancel and retender the work immediately. Retendered with opening 8/2/2021. No offer received. To be retendered. |  |  |  | 0.021
15 | 25 | 17-18 | KER-THI-044 | Providing mechanical Sludge drying unit at Muttathara 107 Mld STP | 2018-01-01 | 5 | Work order issued on 25/01/2021. |  |  |  | 0.0507
|  |  |  | TOTAL - SEWERAGE |  | 131.06 |  |  |  |  | 28.6446
PH DIVISION NORTH, TRIVANDRUM
WATER SUPPLY SECTOR
1 |  | 17-18 |  | Replacement of the existing damaged pipe lines & Alteration of house connections of Thiruvananthapuram water supply scheme | 13/11/2017 | 15 | Work split in to 32 packages, Out of this, 20 packages executing by PH Division North & 12 packages executing by PH Division South
| 1 | 17-18 | KER-THI-058 | Replacing existing 100 mm AC along Chakkalamukku - Societymukku |  | 3.2294 | Work completed | 100% | Completed |  | 3.507
| 2 | 17-18 | KER-THI-059 | Replacing existing 125 mm AC along Pipinmoodu - Golflinks road |  | 0.5292 | Work completed | 100% | Completed |  | 0.52
| 3 | 17-18 | KER-THI-060 | Replacing existing 80 mm AC along Monvila Ushus Nagar to Chenkodikkadu |  | 0.165 | Work completed | 100% | Completed |  | 0.081
| 4 | 17-18 | KER-THI-061 | Replacing existing 150 mm CI along Mulavan Jn- Gowreesapattom-Pottakuzhy |  | 0.5151 | Work completed | 100% | Completed |  | 0.794
| 5 | 17-18 | KER-THI-062 | Replacing existing 100 mm AC along Mosque lane Pettah ward |  | 0.2818 | Work completed. | 100% | Completed |  | 0.191
| 6 | 17-18 | KER-THI-126 | Replacing existing 80 mm AC along Amabalamukku NCC road |  | 0.5693 | Work completed | 100% | Completed |  | 0
| 7 | 17-18 | KER-THI-127 | Replacing existing 100 mm AC along Vayalikkada - Madathunada road |  | 0.6357 | Work completed. | 100% | Completed |  | 1.286
| 8 | 17-18 | KER-THI-129 | Replacing existing 80 mm AC along Manvila - Pullukadu-Don bosco road |  | 0.1726 | Work completed | 100% | Completed |  | 0.081
| 9 | 17-18 | KER-THI-130 | Replacing existing 80 mm AC along Ambalamukku Mannadi Lane |  | 0.1965 | Work completed. | 100% | Completed |  | 0.214
| 10 | 17-18 | KER-THI-202 | Replacing existing 150 mm AC along Ambalamukku - Oolampara road |  | 0.4269 | Work completed. | 100% | Completed |  | 0.346
| 11 | 17-18 | KER-THI-203 | Replacing existing 100 mm AC along Varambassery road |  | 0.5614 | Work completed. | 100% | Completed |  | 0.825
| 12 | 17-18 | KER-THI-204 | Replacing existing 110 mm PVC along Thilak Nagar Parottukonam |  | 0.229 | Work completed. | 100% | Completed |  | 0.15
| 13 | 17-18 | KER-THI-208 | Replacing existing 100 mm AC along Rajaji Nagar inThampanoor ward |  | 0.4576 | Work completed | 100% | Completed |  | 0.337
| 14 | 17-18 | KER-THI-210 | Replacing existing 150 mm AC along Arasumoodu to Thippatti temple road |  | 0.2923 | Work completed. | 100% | Completed |  | 0.273
| 15 | 17-18 | KER-THI-212 | Replacing existing 50 mm GI along Musaliar lane Pettah ward |  | 0.0729 | Work completed. | 100% | Completed |  | 0.578
| 16 | 17-18 | KER-THI-214 | Replacing existing 80 mm AC along Monvila tank to Thalavarambu Temple road |  | 0.1778 | Work completed | 100% | Completed |  | 0.091
| 17 | 17-18 | KER-THI-215 | Replacing existing 80 mm AC along Monvila Jn to Nirmalalayam road |  | 0.1552 | Work completed. | 100% | Completed |  | 0.074
| 18 | 17-18 | KER-THI-216 | Replacing existing 100 mm AC along Madathunada - Perappoor road |  | 0.3179 | Work completed. | 100% | Completed |  | 0.504
| 19 | 17-18 | KER-THI-218 | Replacing existing 100 mm AC along Vayalikkada to Kuravankonam |  | 0.3455 | Work completed. | 100% | Completed |  | 1.085
| 20 | 17-18 | KER-THI-220 | Replacing existing 100 mm AC along Kunnukuzhi road |  | 0.5654 | Work completed. | 100% | Completed |  | 0.69
2 |  | 17-18 |  | Replacement of old and damaged pipelines of Trivandrum water supply scheme & alteration of house connections -Phase II | 22/02/2018 | 2.5 | Work split in to 7 packages, Out of this, 6 packages executing by PH Division North & 1 package executing by PH Division South
| 21 | 17-18 | KER-THI-244 | Replacing old AC main with 140mm,110mm and 90mm PVC pipes along Sree rangam lane, Elankom gardens, judge lane in Sasthamangalam ward |  | 0.7988 | Work completed | 100% | Completed |  | 0.416
| 22 | 17-18 | KER-THI-247 | Replacing old AC service main pipes with 110mm, 90mm, UPVC Pipes at CSM Nagar in Vazhuthacaud ward, Thiruvananthapuram |  | 0.443 | Work completed | 100% | Completed |  | 0.277
| 23 | 17-18 | KER-THI-249 | Improvement of water supply to Kallampally & Periyamadam area by interconnecting with 110 mm PVC pipe |  | 0.0942 | Work completed. | 100% | Completed |  | 0.519
| 24 | 17-18 | KER-THI-253 | Replacing old AC pipes with 110mm PVC pipes along Gandhi Nagar lane, Tagore Nagar, in Vazhuthacaud Ward, Thruvananthapuram |  | 0.1267 | Work completed | 100% | Completed |  | 0.081
| 25 | 17-18 | KER-THI-256 | Replacing old AC service main pipes with 110mm, 90mm UPVC pipes at Udarasiromany Road and Palottukonam in Vazhuthacaud ward, Thiruvananthapuram |  | 0.63 | Work completed. | 100% | Completed |  | 0.919
| 26 | 17-18 | KER-THI-259 | Replacing old AC service main pipes with UPVC main along Panickers Lane and Mangalam Lane in Sasthamangalam Ward, Thiruvananthapuram |  | 0.2113 | Work completed. | 100% | Completed |  | 0.204
|  |  |  | TOTAL - WATER SUPPLY |  | 12.2005 |  |  |  |  | 14.043
PH DIVISION SOUTH, TRIVANDRUM
WATER SUPPLY SECTOR
1 |  | 17-18 |  | Replacement of the existing damaged pipe lines & Alteration of house connections of Thiruvananthapuram water supply scheme | 13/11/2017 | 15 | Work split in to 32 packages, Out of this, 20 packages executing by PH Division North & 12 packages executing by PH Division South |  |  |  | 3.25
| 1 | 17-18 | KER-THI-225 | Replacement of existing 150mm AC pipe with 160mm pvc at Konchiravila area |  | 0.3948 | Work completed. | 100% | Completed
| 2 | 17-18 | KER-THI-228 | Replacement of existing 150mm AC pipe with 160mm pvc at Sreevaraham area |  | 0.5138 | Work completed. | 100% | Completed
| 3 | 17-18 | KER-THI-232 | Replacement of existing 150mm AC pipe with 160mm pvc at Ariyankuzhy area |  | 0.96 | Work completed. | 100% | Completed
| 4 | 17-18 | KER-THI-233 | Replacement of existing 100mm GI pipe with 110mm pvc at Chalai area |  | 0.685 | Work completed. | 100% | Completed
| 5 | 17-18 | KER-THI-234 | Replacing existing damaged pipe and laying 160 mm pvc and altering existing connection to new line at Puthenkada Jn to Magattukadavu under Thirumala section |  | 0.5469 | Work completed. | 100% | Completed
| 6 | 17-18 | KER-THI-235 | Replacing existing damaged pipe and laying 110 mm pvc and altering existing connection to new line at Mangattukadavu CSI Jn to Annoor under Thirumala section |  | 0.4803 | Work completed. | 100% | Completed
| 7 | 17-18 | KER-THI-237 | Replacing existing damaged pipe and laying 110 mm pvc and altering existing connection to new line at Mangattukadavu to Swathy Nagar under Thirumala section |  | 0.1096 | Work completed. | 100% | Completed
| 8 | 17-18 | KER-THI-239 | Replacing existing damaged pipe and laying 110 mm pvc and altering existing connection to new line at Thirumala to Puthenkada Jn under Thirumala section |  | 0.0276 | Work completed. | 100% | Completed
| 9 | 17-18 | KER-THI-293 | TWSS – Alteration of House connections to the JICA and JnNURM line in Cheriyamuttam area (Package 1) |  | 0.434 | Work in progress | 100% | Completed
| 10 | 17-18 | KER-THI-294 | TWSS – Alteration of House connections to the JICA and JnNURM line in Poonthura church area (Package 2) |  | 0.3182 | Work completed | 100% | Completed
| 11 | 17-18 | KER-THI-295 | TWSS MACE AMRUT Proposal-Providing new connection and alterations of house connection from JICA/JnNURM Project laid lines in Bheemapally, Bheemapally east and Manikavilakam wards under Kuriathy section (Package 3) |  | 0.329 | Work completed | 100% | Completed
| 12 | 17-18 | KER-THI-296 | Replacement of 100mm AC pipes and laying 110mm PVC at Mankeezh line at Sreevaraham under Kuriathy section |  | 0.31 | Work completed | 100% | Completed
2 |  | 17-18 |  | Replacement of old and damaged pipelines of Trivandrum water supply scheme & alteration of house connections -Phase II | 22/02/2018 | 2.5 | Work split in to 7 packages, Out of this, 6 packages executing by PH Division North & 1 package executing by PH Division South
| 13 | 17-18 | KER-THI-262 | Replacing old AC main and Laying of 110 mm PVC 6kg/cm2 pipe at Vellayani Junction,Studio Road to Palnkalamukku, Nemom ward. |  | 0.1876 | Work completed | 100% | Completed |  | 0.2378
|  |  |  | TOTAL |  | 5.2968 |  |  |  |  | 3.4878
SEWERAGE DIVISION, TRIVANDRUM
SEWERAGE SECTOR
1 |  | 15-16 |  | AMRUT - SAAP 2015-16 - Sewerage work in Trivandrum Corporation | 26/03/2016 | 3.72 | Work split in to two packages and these wo main packages have been completed and commissioned. Payment also done. Remaining work of paving interlock tiles in BSF compound, which is not the part of original scope in progress & 80 % completed. This work is arranged as part of the agreement between KWA and BSF for permitting KWA to lay the pipe through BSF compound. |  |  |  | 3.4015
| 1 | 15-16 | KER-THI-002 | Laying 900mm dia DI pumping main at Muttathara Sewage Treatment Plant. |  | 3.34 | Work Completed | 100% | Completed
| 2 | 15-16 | KER-THI-004 | Rehabilitation of existing pump and machineries- Kannammoola pump |  | 0.38 | Work Completed | 100% | Completed
2 | 3 | 15-16 | KER-THI-003 | Laying 700mm dia RCC NP3 Pipe sewer trunk main II from Murinjapalam – Kannamoola. | 23/02/2017 (16/10/2020 Revised A.S) | 1.64 | Work started. 45 m pipe laid (Out of 394 m) | 13% | 2021-04-30
3 |  | 16-17 |  | Rehabilitation of existing networks in various blocks of Thiruvananthapuram sewerage scheme | 2017-02-11 | 3.84 | Split in to 23 works and all are completed |  |  |  | 3.368
| 4 | 16-17 | KER-THI-166 | AMRUT - TSS Rehabilitation -Increasing the capacity of sewer 150mm dia SW pipe to 200mm dia SW pipe and construction of RCC manholes at Manacadu Harshan Nagar and Seethapuram lane. |  | 0.1447 | Work completed. (3 works clubbed, Sl No:4, 5, 6) | 100% | Completed
| 5 | 16-17 | KER-THI-193 | AMRUT -TSS Rehabilitation - Urgent Re-Laying 200mm SW pipe and construction of manhole near Parthas at Power House Road . |  | 0.0586 | Work completed. (3 works clubbed, Sl No:4, 5, 6) | 100% | Completed
| 6 | 16-17 | KER-THI-194 | AMRUT - TSS Rehabilitation - Relaying chocked and broken sewer line including construction of man holes from SNRA 88B to SNRA 101 at SN Nager, Pettah and and reconstruction of dilapidated man holes at Ambalathumukku Kaumudhi Resiedents Lane |  | 0.0576 | Work completed. (3 works clubbed, Sl No:4, 5, 6) | 100% | Completed
| 7 | 16-17 | KER-THI-190 | AMRUT - TSS Rehabilitation - Providing 200mm sewer line from VRA B - 26 to VRA A -22 and connectig to the existing MH near Khadi Board, Vanchiyoor |  | 0.0481 | Work completed. (3 works clubbed, Sl No:7,8) | 100% | Completed
| 8 | 16-17 | KER-THI-191 | AMRUT- TSS Rehabilitation - Relaying damaged 300mm sw pipe from Parachal Jn in Malloor road to Devi pharma Junction and construction of dilapidated man holes at Thumbara lane in Vanchiyoor ward |  | 0.1855 | Work completed. (3 works clubbed, Sl No:7,8) | 100% | Completed
| 9 | 16-17 | KER-THI-192 | AMRUT- TSS Rehabilitation - Reconstruction of dilapidated man holes at Ambujavilasom, malloor road, Chettikulangara, Athani, Amba nagar, Mullassery, Chirakkulam, Thengapura, Mulluvilakom, Pettah, Rishimangalam, Palkulangara, Chempakassery, Kaithamukku, Pattoor etc under Sewerage Section I, Kuriyathy |  | 0.3095 | Work Completed | 100% | Completed
| 10 | 16-17 | KER-THI-195 | AMRUT - TSS Rehabilitation -D Block - Supplying and laying 200 mm dia SW sewer branch line from The Existing MH towards Chalakuzhy - Kappil road |  | 0.175 | Work completed. | 100% | Completed
| 11 | 16-17 | KER-THI-196 | TSS - AMRUT -Rehabilitation --Laying 150mm SW pipe at Aiswarya lane, Poornima lane, Bharath lane, Mythri lane & Kavuvila lane at Sasthamangalam ward under sewerage section Sasthamangalam |  | 0.3155 | Work completed. | 100% | Completed
| 12 | 16-17 | KER-THI-197 | AMRUT -TSS Rehabilitation - Increasing the size of existing sewer main using 400mm dia RCC NP3 pipe from Edappazhinji towards CSM Nagar I Reach Ch.0 M to 379m |  | 0.83 | Work completed. (3 works clubbed, Sl No:12,13,14) | 100% | Completed
| 13 | 16-17 | KER-THI-198 | AMRUT-TSS Rehabilitation -Increasing in size of existing sewer main using 400mm dia RCC NP3 pipe from Edappazhinji towards CSM Nagar II Reach Ch.379M to 817m |  | 0.718 | Work completed. (3 works clubbed, Sl No:12,13,14) | 100% | Completed
| 14 | 16-17 | KER-THI-199 | AMRUT-TSS Rehabilitation - Increasing in size of existing sewer main using 300mm dia SWpipe from Edappazhinji towards CSM Nagar III Reach Ch.817M to 1191m |  | 0.375 | Work completed. (3 works clubbed, Sl No:12,13,14) | 100% | Completed
| 15 | 16-17 | KER-THI-200 | AMRUT-TSS Rehabilitation - Dismantling of damaged brick manhole and re-constructing with RCC manhole at Jawahar Nagar area under Sewerage Section Sasthamangalam |  | 0.066 | Work completed. | 100% | Completed
| 16 | 16-17 | KER-THI-201 | AMRUT -TSS Rehabilitation - Dismantling of damaged brick manhole and re-constructing with RCC manhole at Kanaka Nagar area under Sewerage Section Sasthamangalam |  | 0.065 | Work completed. | 100% | Completed
| 17 | 16-17 | KER-THI-205 | AMRUT-TSS Rehabilitation - Dismantling of damaged brick manhole and re-constructing with RCC manhole at Lenin Nagar |  | 0.065 | Work completed. (3 works clubbed, Sl No:17,18,19) | 100% | Completed
| 18 | 16-17 | KER-THI-206 | AMRUT-TSS Rehabilitation - Dismantling rxisting damaged 100mm dia Sw sewer line and laying 200mm dia SW pipe and construction of manholes at Madathuvila Lane Edappazhinji |  | 0.0225 | Work completed. (3 works clubbed, Sl No:17,18,19) | 100% | Completed
| 19 | 16-17 | KER-THI-227 | TSS - AMRUT -Rehabilitation -- Dismantling of damaged brick manhole and re-constructing with RCC manhole at Attara lane, Kannammoola under Sewerage Section Sasthamangalam |  | 0.044 | Work completed. (3 works clubbed, Sl No:17,18,19) | 100% | Completed
| 20 | 16-17 | KER-THI-229 | AMRUT -TSS Rehabilitation - Dismantling of damaged brick manhole and re-constructing with RCC manhole at Nanthancodu Nalanda area under Sewerage Section Sasthamangalam |  | 0.065 | Work completed. | 100% | Completed
| 21 | 16-17 | KER-THI-230 | AMRUT-TSS Rehabilitation -- Dismantling of damaged brick manhole and re-constructing with RCC manhole at Peroorkada - Ambalamukku area under Sewerage Section Sasthamangalam |  | 0.064 | Work completed. | 100% | Completed
| 22 | 16-17 | KER-THI-231 | AMRUT -TSS Rehabilitation - Dismantling of damaged brick manhole and re-constructing with RCC manhole at Poojappura Thirumala road |  | 0.06 | Work completed. | 100% | Completed
| 23 | 16-17 | KER-THI-236 | AMRUT - TSS Rehabilitation- Urgent rehabilitation works on the sewerage system at Cherukode lane, Kunchalummoodu |  | 0.078 | Work completed ( 4 works clubbed, Sl No:23 to 26) | 100% | Completed
| 24 | 16-17 | KER-THI-238 | AMRUT- TSS Rehabilitation- Urgent rehabilitation works on the sewerage system at Kadakamthalackal lane, Melaranoor |  | 0.034 | Work completed ( 4 works clubbed, Sl No:23 to 26) | 100% | Completed
| 25 | 16-17 | KER-THI-240 | AMRUT -TSS Rehabilitation - Urgent rebalitation of dilapidated manholes at Karamana Mangad lane (KMRA) |  | 0.041 | Work completed ( 4 works clubbed, Sl No:23 to 26) | 100% | Completed
| 26 | 16-17 | KER-THI-241 | AMRUT - TSS- Rehabilitation- Urgent reconstruction of dilapidated old brick manholes at Nandavanam Gardens, Valiyasala |  | 0.018 | Work completed ( 4 works clubbed, Sl No:23 to 26) | 100% | Completed
4 |  | 16-17 |  | Providing new network in the missing areas of the core city in Thiruvananthapuram | 2017-02-11 | 7.98 | Split in to 14 works out of this 10 nos completed.
| 27 | 16-17 | KER-THI-075 | Tss- E Block Zone II - Laying 700mm dia sewer main from Jagathy towards common manhole at Vivekananda Nagar Ist Reach ch 0m to 259m |  | 0.895 | 209 m pipe laid, 11 nos of MH completed and 2 nos under construction. (2 works clubbed, Sl No:27 & 28) | 66% | 2021-03-31 |  | 0.752
| 28 | 16-17 | KER-THI-076 | Tss- E Block Zone II - Laying 700mm dia sewer main from Jagathy towards common manhole at Vivekananda Nagar IInd Reach ch 259m to 512m |  | 0.995 | Work in progress. (2 works clubbed, Sl No:27 & 28) | 66% | 2021-03-31
| 29 | 16-17 | KER-THI-125 | TSS- D Block zone II - Laying 600mm dia RCC NP3 pipe sewer main from Edappazhinji to Chithranagar via vettamukku - 1. |  | 0.62 | Work completed (2 works clubbed, Sl No:29 & 30) | 100% | Completed |  | 0.701
| 30 | 16-17 | KER-THI-128 | TSS- D Block zone II - Laying 600mm dia RCC NP3 pipe sewer main from Edappazhinji to Chithranagar via vettamukku - 2. |  | 0.535 | Work completed (2 works clubbed, Sl No:29 & 30) | 100% | Completed
| 31 | 16-17 | KER-THI-131 | TSS E Block Zone II Laying 300mm dia SW Pipe sewer main from Jagathy Vettamukku sewer main MH 60 towards Koottamvila Ex.MH (N-N1) |  | 0.19 | Work completed | 100% | Completed |  | 0.174
| 32 | 16-17 | KER-THI-132 | TSS- E Block Zone III - Supplying and laying 200 mm dia SW pipe branch sewer line from the existing Konathukulangara lane towards Padayani road ( PRA - lane10) at Maruthankuzhy |  | 0.143 | Work completed (3 works clubbed, Sl No:32, 33, 34) | 100% | Completed |  | 0.203
| 33 | 16-17 | KER-THI-134 | TSS- E Block Zone III - Supplying and laying 150 mm dia SW branch sewer line from the existing MH towards Melekuzhivila at Maruthamkuzhy |  | 0.027 | Work completed (3 works clubbed, Sl No:32, 33, 34) | 100% | Completed
| 34 | 16-17 | KER-THI-136 | TSS- E Block Zone III - Supplying and laying 200 mm dia SW pipe branch sewer line from the existing Konathukulangara line towards Padayani road association lane No. 05 ( PRA 16-20) at Maruthankuzhy |  | 0.097 | Work completed (3 works clubbed, Sl No:32, 33, 34) | 100% | Completed
| 35 | 16-17 | KER-THI-133 | Supplying and laying 200 mm dia SW sewer line from The Existing MH towards Binoy lane at Kizhakke Pattom Residence Association |  | 0.077 | Work completed | 100% | Completed |  | 0.063
| 36 | 16-17 | KER-THI-135 | TSS-Supplying and laying 200 mm dia SW pipe sewer line from Padayani Road Ex: MH towards Padayani Gardens Lane No. 8A ( PRA G1 to G17) |  | 0.118 | Work completed (2 works clubbed, Sl No:36 & 37) | 100% | Completed |  | 0.201
| 37 | 16-17 | KER-THI-139 | TSS- E Block Zone III - Supplying and laying 200 mm dia SW pipe branch sewer line from the existing Konathukulangara sewer main towards Dwani Lane ( PRA Lane No.07) at Maruthankuzhy |  | 0.151 | Work completed (2 works clubbed, Sl No:36 & 37) | 100% | Completed
| 38 | 16-17 | KER-THI-142 | TSS - E Block Zone II - Laying 300mm dia SW Sewer main interconnection between Kootanvila and Chittatinkara Sewer main. |  | 0.0975 | Work completed. | 100% | Completed |  | 0.056
| 39 | 16-17 | KER-THI-289 | TSS-Urgent laying of 300mm dia HDPE. pipe and construction of new manholes at Chengalloor and Vattavila of Punnakkamugal ward. |  | 1.03 | 600 mtr pipes arrived at site. Levels and Manholes for reconstruction are fixed. Laying is set to start.. |  | 2021-05-30
| 40 | 16-17 | KER-THI-164 | TSS - Laying 250 mm dia DI K9 pumping main from Mudavanmugal Pump House to Jagathy Junction and construction of Stilling Chamber at Jagathy Junction |  | 3 | Agreement executed . Pipe supplied. |  | 2021-05-31 | PWD - 250mm dia pipe 1350m - BM&BC road cutting required. Restoration Charge (Rs.66.40Lakhs) remitted on 25/4/2019. Addressed Deputy Collector regarding the issue. Written permission from District Collector obtained recently. (9/10/2020) | 1.217
5 | 41 | 17-18 | KER-THI-046 | Providing new networks (Sewerage facility in the Kalladimugham Housing Colony) | 1/1/2018 16/9/2020 (Revised A.S) | 13.15 | 350mm DI Pumping main , out of 4400 m, 1812m has been laid. 150mm SW Pipe 659m laid 40 Man holes have been completed, 8 Nos under construction. 250 mm SW Pipe 86 m laid 5 nos Man Hole completed Well works under progress. | 43% | 2021-05-30 | Due to public agitation taking trial pit for laying of pumping main in front of PoonthuraPuthen pally has been stopped. Addressed the matter to Hon: Mayor, Mission Director, SMMU-AMRUT for urgent intervention. Sanction from NHAI pending. 350 mm DI pipe (Casing - 800mm dia MS pipe) 50 m near Kumarichantha Market - Through HDD method (Depth comes to 2.5m) For NHAI road cutting request submitted on 10/10/2019. Later, online application submitted to NHAI for carrying through HDD method on 13/3/2020.NHAI has given the letter for remitting bank guarantee via email on 19.10.20 for processing the request. Bank guarantee remitted. Awaiting sanction | 3.319
6 |  | 17-18 |  | Providing new network in the missing areas of core city | 2018-01-01 | 9.95 | Work split into 46 packages, 40 completed
| 42 | 17-18 | KER-THI-217 | AMRUT SAAP -2017-18 -TSS- Laying 200 mm SW sewer line in Kuravankonam , Vikramapuram Hills house no.VH-130 to 135- under Sewerage Section,Sasthamangalam |  | 0.0733 | Work Completed | 100% | Completed |  | 0.046
| 43 | 17-18 | KER-THI-219 | AMRUT SAAP -2017-18 -TSS- Laying 200 mm SW sewer line from Jawahar nagar O street towards Bhagavathy nagar A street- under Sewerage Section,Sasthamangalam |  | 0.115 | Work Completed | 100% | Completed |  | 0.061
| 44 | 17-18 | KER-THI-221 | AMRUT SAAP -2017-18 -TSS- Laying 200 mm SW sewer line in Kowdiar ward , Kadappathala line from MGRA-46 to 53- under Sewerage Section,Sasthamangalam |  | 0.0973 | Work Completed | 100% | Completed |  | 0.398
| 45 | 17-18 | KER-THI-223 | AMRUT SAAP -2017-18 -TSS- Laying 200 mm SW sewer line in Kowdiar ward , Kadappathala line from MGRA-82 to 92- under Sewerage Section,Sasthamangalam |  | 0.0909 | Work Completed | 100% | Completed
| 46 | 17-18 | KER-THI-226 | AMRUT SAAP -2017-18 -TSS- Laying 200 mm SW sewer line in Kowdiar ward , Bhagavathi line B-7- under Sewerage Section,Sasthamangalam |  | 0.1618 | Work Completed | 100% | Completed
| 47 | 17-18 | KER-THI-243 | AMRUT SAAP -2017-18 -TSS- Dismantling existing 100 mm dia SW pipe and relaying 200 mm SW sewer line and construction of RCC Man hohes at T N line , Vazhuthakadu under Sewerage Section,Sasthamangalam |  | 0.1466 | Work Completed | 100% | Completed
| 48 | 17-18 | KER-THI-245 | AMRUT SAAP -2017-18 -TSS- Laying 200 mm SW sewer line in Nethaji Bose road , Marappalam near Keni bridge from NBRA H 1 to NBRA H - 10 under Sewerage Section,Sasthamangalam |  | 0.0828 | Work Completed | 100% | Completed
| 49 | 17-18 | KER-THI-246 | AMRUT SAAP-2017-18- TSS- Supplying & Laying sewer line at Street - 3 of Devaswom Board Residents Association Area |  | 0.095 | Work Completed | 100% | Completed
| 50 | 17-18 | KER-THI-222 | AMRUT SAAP -2017-18 -TSS- Laying 200 mm SW sewer line in Kowdiar ward , Kadappathala line from MGRA-56 to 72- under Sewerage Section,Sasthamangalam |  | 0.1514 | Work Completed | 100% | Completed |  | 0.091
| 51 | 17-18 | KER-THI-224 | AMRUT SAAP -2017-18 -TSS- Laying 200 mm SW sewer line in Kowdiar ward , Bhagavathi line C-15 and C-16- under Sewerage Section,Sasthamangalam |  | 0.189 | Work Completed | 100% | Completed |  | 0.106
| 52 | 17-18 | KER-THI-248 | AMRUT SAAP -2017-18 -TSS- Raising of manholes under tarred surface and replacing of RCC cover slabs with C I M H cover with frame in Right R C area -under Sewerage Section, Sasthamangalam |  | 0.1277 | Work completed. | 100% | Completed |  | 0.14
| 53 | 17-18 | KER-THI-250 | AMRUT SAAP -2017-18 -TSS- Raising of manholes under tarred surface and replacing of RCC cover slabs with C I M H cover with frame in Central R C area - under Sewerage Section,Sasthamangalam |  | 0.1269 | Work completed. | 100% | Completed |  | 0.139
| 54 | 17-18 | KER-THI-251 | AMRUT SAAP -2017-18 -TSS- Raising of manholes under tarred surface and replacing of RCC cover slabs with C I M H cover with frame in Left R C area - under Sewerage Section,Sasthamangalam |  | 0.1118 | Work completed. | 100% | Completed |  | 0.123
| 55 | 17-18 | KER-THI-254 | AMRUT SAAP -2017-18 -TSS- Raising of manholes under tarred surface and replacing of RCC cover slabs with C I M H cover with frame in West R C area - under Sewerage Section,Sasthamangalam |  | 0.1024 | Work completed. | 100% | Completed |  | 0.113
| 56 | 17-18 | KER-THI-255 | AMRUT SAAP 2017-18 - Rehabilitation- Dismantling of damaged brick manhole and re constructing with RCC manhole in Right R C area under Sewerage section , Sasthamangalam |  | 0.1048 | Work completed. | 100% | Completed |  | 0.283
| 57 | 17-18 | KER-THI-257 | AMRUT SAAP 2017-18 - Rehabilitation- Dismantling of damaged brick manhole and re constructing with RCC manhole in Central R C area under Sewerage section, Sasthamangalam |  | 0.1078 | Work completed. | 100% | Completed
| 58 | 17-18 | KER-THI-258 | AMRUT SAAP 2017-18 - Rehabilitation- Dismantling of damaged brick manhole and re constructing with RCC manhole in Left R C area under Sewerage section , Sasthamangalam |  | 0.0991 | Work completed. | 100% | Completed
| 59 | 17-18 | KER-THI-260 | AMRUT SAAP 2017-18 - Rehabilitation- Dismantling of damaged brick manhole and re constructing with RCC manhole in West R C area under Sewerage section , Sasthamangalam |  | 0.0916 | Work completed. | 100% | Completed |  | 0.08
| 60 | 17-18 | KER-THI-261 | TSS - Reconstruction of dilapidated manholes in Palkulangara, Pettah, Perunthanni area under Sewerage Sn 1 |  | 0.21 | Work completed. | 100% | Completed |  | 0.202
| 61 | 17-18 | KER-THI-263 | TSS - Reconstruction of dilapidated manholes in Manacaud, Sreevaraham, Kalippankulam, Enchakkal area under Sewerage Sn 1 |  | 0.21 | (3 works clubbed, Sl No:61 to 63) Completed | 100% | Completed |  | 0.278
| 62 | 17-18 | KER-THI-264 | TSS - Reconstruction of dilapidated manholes in Chalai, Fort, Chenthitta, Attukal, Pazhavangadi, Powerhouse area under Sewerage Sn 1 |  | 0.21 |  | 100% | Completed
| 63 | 17-18 | KER-THI-265 | TSS - Reconstruction of dilapidated manholes in Vanchiyoor, Pulimoodu, chirakulam, Uppidamoodu, Pallimukku area under Sewerage Sn 1 |  | 0.21 |  | 100% | Completed
| 64 | 17-18 | KER-THI-266 | TSS - Raising of Manhole covers in various wards under Sewerage Sn. 1 |  | 0.2 | Work completed. | 100% | Completed |  | 0.209
| 65 | 17-18 | KER-THI-267 | TSS - Providing Sewerage facility to Eastern side of Amayizhanjan thodu between Vanchiyoor Jn and Samad Hospital road jn |  | 0.21 | Agreement executed on 13/11/2020 SI No: 65 - Trial pit excavation arranged on 17/02/2021.. SI no: 66 - 190/475 M pipe laying and 2/35 MH construction completed, work in progress SI No: 67 - 50 M/89 M laying and 2/6 MH construction completed, work in progress |  | 2021-05-18
| 66 | 17-18 | KER-THI-268 | TSS-Rehabilitation of sewer line including cleaning, replacing damaged lines etc at Kozhiyottu, Vilayil lane, Kaithamukku, Thengappura area |  | 0.4 |  | 40% | 2021-05-18
| 67 | 17-18 | KER-THI-270 | TSS- Rehabilitation of damaged sewer network in Amma Residents area, Palkulangara |  | 0.09 |  | 56% | 2021-05-18 | Tar cut sanction denied by PWD in West Fort - Kanjiravilakom road stating road under DLP.
| 68 | 17-18 | KER-THI-271 | TSS- Rehabiliatation of sewer line from Pettah to Railway hospital road |  | 0.5 | Work completed. | 100% | Completed |  | 0.077
| 69 | 17-18 | KER-THI-272 | TSS-Rehabilitation and upgradation of existing sewer network at Thakaraparambu, Sreekanteswaram Manacaud Aiswarya Nagar Area |  | 0.4 | Work in progress (2 works clubbed, Sl No: 69 & 70) Si No: 69 - 551/551 M pipe laying & 24/24 MH construction completed. SI no: 70 - 402/600 M pipe laying completed,2 out of 2 MH construction completed at Chattambi swamy lane. | 100% | Completed |  | 0.02
| 70 | 17-18 | KER-THI-273 | TSS-Rehabilitation and upgradation of existing sewer network at Enchakkal area |  | 0.4 |  | 67% | 2021-02-28
| 71 | 17-18 | KER-THI-274 | TSS - Reconstruction of dilapidated manholes in Arannoor, Thycaud area under Sewerage Sn 2 |  | 0.2 | Work completed | 100% | Completed |  | 0.597
| 72 | 17-18 | KER-THI-275 | TSS - Reconstruction of dilapidated manholes in Karamana Thaliyal area under Sewerage Sn 2 |  | 0.2 | Work completed | 100% | Completed
| 73 | 17-18 | KER-THI-276 | TSS - Reconstruction of dilapidated manholes in Poojapura, Mudavanmugal area under Sewerage Sn 2 |  | 0.2 | Work completed | 100% | Completed
| 74 | 17-18 | KER-THI-277 | AMRUT SAAP -2017-18-TSS Rehabilitation and up gradation of Existing sewer net work at Karamana Sathya Nagar Branch lanes of Sreedevi Nagar under Sewerage Section No.2, Kuriathy |  | 0.25 | Work completed. | 100% | Completed |  | 0.324
| 75 | 17-18 | KER-THI-286 | TSS-Rehabilitation and upgradation of existing sewer network at Punnen road near secratariat and Mele Thampanoor area |  | 0.14 | Work completed | 100% | Completed
| 76 | 17-18 | KER-THI-278 | TSS - Raising of Manhole covers in various wards under Sewerage Sn. 2 |  | 0.2 | Work completed. | 100% | Completed |  | 0.214
| 77 | 17-18 | KER-THI-279 | TSS-Rehabilitation and upgradation of existing sewer network at Jagathy kavuvila, Karyakar lane, Valiyasala kavil temple, Arysala Vivekananda street, Vilayil lane, Erakkam road |  | 0.35 | Work completed. | 100% | Completed |  | 0.53
| 78 | 17-18 | KER-THI-280 | TSS-Rehabilitation and upgradation of existing sewer network and interconnections at Valiyasala myladikadavu, Jagathy near sunny pharma, CIT road |  | 0.19 | Work completed. | 100% | Completed
| 79 | 17-18 | KER-THI-287 | TSS- Rehabiliatation of sewer line at Melemankattukonam in Nedumcad ward |  | 0.24 | Work completed | 100% | Completed
| 80 | 17-18 | KER-THI-281 | TSS-Rehabilitation and upgradation of existing sewer network at Kala vihar, Kunnukuzhy |  | 0.5 | Work completed. | 100% | Completed |  | 0.303
| 81 | 17-18 | KER-THI-282 | TSS-Rehabilitation and upgradation of existing sewer network at Pattom Vrindavan gardens |  | 0.07 | Work completed. | 100% | Completed |  | 0.473
| 82 | 17-18 | KER-THI-283 | TSS-Rehabilitation and upgradation of existing sewer network at Thittakudi temple lane, Vadakkekottah, Puthunagar area |  | 0.56 | Work completed. | 100% | Completed
| 83 | 17-18 | KER-THI-284 | TSS-Rehabilitation and upgradation of existing sewer network at Kunninpuram, Vivekananda nagar, Kailas nagar, NM nagar area |  | 0.56 | Work completed | 100% | Completed |  | 0.398
| 84 | 17-18 | KER-THI-285 | AMRUT SAAP 17-18 - TSS- Rehabilitation and up gradation of Existing sewer net work at TRWA area, Podiyadi lane, BRWA area Anil Nagar, Ayilliathu Finance road In Thalial area under sewerage Section No:2 Kuriathy. |  | 0.4 | Work completed | 100% | Completed |  | 0.404
| 85 | 17-18 | KER-THI-288 | TSS- Rehabiliatation of sewer line at Thoppil lane, Valiyasala, Sasthri nagar West, cherukodu, Thelunguchettitheruvu area |  | 0.16 | Work in progress, nearing completion. | 95% | 2021-02-03 | NH permission required | 0.001
| 86 | 17-18 | KER-THI-269 | TSS-Rehabilitation and upgradation of existing sewer network at Manjalikulam branch road, Ootukuzhy, Vanrose jn branch road |  | 0.34 | Trial pits completed, Execution started from lower end at Mele Thampanoor | 8% | 2021-05-30
| 87 | 17-18 | KER-THI-252 | TSS-Rehabilitation and upgradation of existing sewer network at Thycadu MG Radhakrishnan Jn towards Poundkulam |  | 0.27 | Work completed | 100% | Completed |  | 0.171
7 | 88 | 17-18 | KER-THI-056 | Providing sewerage facility to newly constructed residential colony at Karimadom- Part II | 22/2/2018 | 0.353 | Work completed | 100% | Completed |  | 0.142
|  |  |  | TOTAL |  | 40.633 |  |  |  |  | 19.3785
KOLLAM
WATER SUPPLY SECTOR
PH DIVISION, KOLLAM
1 |  | 15-16 |  | AMRUT - SAAP 2015-16 - Water supply works in Kollam Corporation | 26/3/2016 | 6.59 | Work split into 8 packages
| 1 | 15-16 | KER-KOL-004 | Replacement of contaminated AC pipe lines in Kollam Corporation - Laying distribution main from Pazhayattukuzhy OHSR to Ammannada Division in Kollam Coporation(250mm DI K9 pipe -2500m). |  | 1.4218 | Work Completed | 100% | Completed |  | 0.96
| 2 | 15-16 | KER-KOL-065 | Extension of 250mm DI K9 pipe line from Madan Nada Junction to Polayathodu Junction in Kollam Corporation 250mm DI K9 pipe- 1000m). |  | 0.71608 | Work Completed | 100% | Completed |  | 0.87
| 3 | 15-16 | KER-KOL-066 | Replacement of contaminated AC pipe lines in Kollam Corporation - Laying distribution main from Andamukkam, Thamarakulam, Contonment area from OH tank near Parvathy mill, Chinnakada to Mundakkal beach area from no: 3/4 (250mm DI K9 pipe -3500, 110mm PVC - 2500m, 63mm ASTM pipe - 750m). |  | 2.8363 | Work completed. | 100% | Completed |  | 2.67
| 4 | 15-16 | KER-KOL-067 | Improvement of Kollam WSS Division No. 7 to 11 in Kollam Corporation (Laying 110mm PVC 2500m, 90mm PVC 4500m). |  | 0.65381 | Work completed. | 100% | Completed |  | 0.404
| 5 | 15-16 | KER-KOL-068 | Improvement of Kollam WSS Division No. 7 to 11 in Kollam Corporation - Replacement of damaged pumpset. |  | 0.1017 | Work completed. | 100% | Completed |  | 0.076
| 6 | 15-16 | KER-KOL-069 | Replacement of 50HP/75HP VT pumpsets at booster pumphouse at Ananathavalleeswaram. |  | 0.5656 | Work completed. | 100% | Completed |  | 0.548
| 7 | 15-16 | KER-KOL-070 | Supply,errection and commissioning of Chlorinator system to Tubewell pumphouses in Kollam corporation. |  | 0.17227 | Work completed. | 100% | Completed |  | 0.089
| 8 | 15-16 | KER-KOL-071 | Supply,erection and commissioning of Chlorinator system to booster pumphouse at Ananathavalleeswaram with supply of 100Kg Chlorine cylinder. |  | 0.11935 | Work completed. | 100% | Completed |  | 0.086
2 | 9 | 16-17 | KER-KOL-014 | Providing new water connection in Kollam Corporation 2016-17. | 15/08/2017 | 7 | Out of 10000 water connections, 8324 Nos of water connections given. As per the demand of Kollam corporation during the core committee meeting held on 12.06.2020, additional 1676 nos of connections from the list of consumers in the 2nd phase of AMRUT SAAP year 16-17 is incorporated and submitted before 25th SHPSC and 26th SHPSC for an amount of Rs.9.2752 Crores for getting revised A.S including tender excess of 5.64%. 26th SHPSC held on 17.12.2020 accorded revised A.S with the condition that half of the tender excess shall be borne by the Corporation. | 83% | 2021-04-15 |  | 6.83
3 | 10 | 17-18 | KER-KOL-026 | Providing new water connection in Kollam Corporation 2017-18. | 13/11/2017 | 7.9 | Work in progress 1978 connections given (Out of 5820 connections) and work is in progress | 34% | 2021-05-28
|  |  |  | TOTAL |  | 21.49 |  |  |  |  | 12.533
PROJECT DIVISION KOLLAM
WATER SUPPLY SECTOR
1 |  | 15-16-17-18 |  | Augumentation of water supply scheme Kollam 2015-16, 2016-17, 2017-18 ( Revised AS vide G.O(Rt) No: 31/2020/LSGD Dated 03/01/2020) | 28/9/2017 & Revised AS on 03/01/2020 | 92.08 | Work split into 6 packages
| 1 | 15-16-17-18 | KER-KOL-007 | Construction of weir at Njankadavu across Kallada river |  | 25.856 | Agreement executed on 04/06/2020. Work is executing through Irrigation Department. Pile load testing work in progress | 2% | 2021-12-03 | The height of ring bund has been increased to 9m at the centre portion of the river, which was only 4m at the time of investigation. Contractor informed his unwillingness to continue the work of ring bund at the sanctioned rate as the total cost of construction of ring bund alone will cost more than Rs. 7.21 crores + GST, instead of Rs.1.98 Cr, the sanctioned amount. Requested Mission Director, SMMU-AMRUT to form a high level expert committee including a representative from KWA, Irrigation, SMMU and CTE for evaluating the claim of the contractor. | 0.0351
| 2 | 15-16-17-18 | KER-KOL-064 | Supplying laying commissioning and maintaining 500mm DI K9 CWPM from TP to OHSR at Vadakkevila (3520m) |  | 4.331 | The work completed except 1000 m. road restoration work (Kollam corporation road). It was included in PWD Budget Work & now it is in Tendering Stage. | 100% | 2021-02-03 |  | 3.093
| 3 | 15-16-17-18 | KER-KOL-015 | Design, Construction, Commissioning and maintaining of 100MLD WTP at Vasoorichira |  | 57.116 | Shuttering work for pedastal column.PCC work and reinforcement work for raft in progress at filter house area.At CFL2 boring 39 nos and casting 38 nos completed.. | 8% | 2022-03-30 |  | 0
| 4 | 15-16-17-18 | KER-KOL-073 | Clear Water Pumping main from WTP to 20LL OHSR at TP using 350mm DI,125 m |  | 0.0999 | Work order issued. But the bidder informed that he is not willing to execute the work at LMR . Hence, cancelled. Work retendered on 29/01/2021 |  |  |  | 0
| 5 | 15-16-17-18 | KER-KOL-074 | Transformer powerline extension at TP site (KSEB work) |  | 2.75 | This work executed through KSEB.Out of 4.5 km's of power line extension at Njankadavu 4.2 km's of work has completed. The balance will be done as ABC due to public objection in cutting newly tarred road at Kulakkada panchayath. Only power line extension is considered in AMRUT - Power station, transformer, retaining wall etc were proposed in KIIFB . | 85% | 2021-02-03 |  | 2.419
| 6 | 15-16-17-18 | KER-KOL-072 | Construction of 12m dia intake well at Njankadavu |  | 1.927 | Work completed | 100% | Completed |  | 1.776
|  |  |  | TOTAL - WATER SUPPLY |  | 92.08 |  |  |  |  | 7.3231
SEWERAGE SECTOR
1 | 1 | 15-16-17 | KER-KOL-017 | Sewage Treatment plant - Kureepuzha | 22/2/2018 & Revised AS on 17/06/2020 | 31.92 | Tree valuation obtained from Social forestry and auction to be done by Kollam Corporation. Structural design under scrutiny in WASCON. | 2% | 27/10/2021 |  | 0.022
WATER SUPPLY SECTOR
PROJECT DIVISION ALAPPUZHA
1 |  | 15-16 |  | Augmentation & Modernization of Water Supply Distribution System in Alappuzha Municipality (Phase-I) | 23/2/2017 | 33.9 | Work split in to 8 packages
| 1 | 15-16 | KER-ALA-210 | Construction of 21 LL Capacity OHSR at Kommadi (Zone-1) |  | 9.314 | Completed | 100% | Completed |  | 4.385
| 2 | 15-16 | KER-ALA-212 | Construction of 12.00LL Capacity OHSR at Thathampally (Zone-IV) |  | 6.5308 | OHSR work has been completed including painting. But for commissioning the OHSR, the work of transmission main under Phase ll need to be completed. Awaiting permission from PWD cut open the road. Transmission main is 500m-300mm dia and can be completed in 15 days on getting Permission from PWD. After completing the same, the OHSR can be commissioned. | 98% | 2021-03-03 |  | 2.778
| 3 | 15-16 | KER-ALA-213 | Construction of 10 LL Capacity OHSR at Pazhavangadi (Zone-VI) |  | 5.7471 | Work completed | 100% | Completed |  | 3.05
| 4 | 15-16 | KER-ALA-211 | Construction of 28 LL Capacity OHSR at Aalissery(Zone-VII) |  | 11.3636 | 3rd level slab concrete completed. Beam reinforcement started. | 50% | 2021-07-30 |  | 4.51
| 5 | 15-16 | KER-ALA-214 | Digital Survey & Design of Network |  | 0.50237 | Work completed | 100% | Completed |  | 0.15
| 6 | 15-16 | KER-ALA-215 | Providing Bulk Meters |  | 0.12057 | The work was tendered on 06/,2/2019 and the tender cancelled as per the direction of Chief Engineer[CR), Kochi. Retendered on 29/05/2020, the lowest bidder quoted 18% above the TPAC. As per the directions from the Chief Engineer, the work order was issued to the lowest bidder to execute the work at the LMR rate which is 9.17 %o lower than the quoted rate (Rs.1018397 /-). Now the bidder declined to accept the work order and pleaded for getting exemption from the work. Retendered with opening date 12/02/2021. |  |  |  | 0
| 7 | 15-16 | KER-ALA-216 | Setting up 24 x 7 Customer Care Facility |  | 0.20095 | The work was tendered on 09/01/2020, and extended to 29/01/2020 since no offers were received. Later the work was retendered on 15/02/2020 and extended to 29/02/2020 and no offers were received. Now it is planned to setting up the customer care with the proposed office building at Allisery OHSR site. The work of the customer care can be carried out after completing the ground floor of the OHSR. Retendered with opening date 18/02/2021. |  |  |  | 0
| 8 | 15-16 | KER-ALA-217 | Setting up Water Kiosks |  | 0.12057 | Completed. Trial run to be done. | 99% | 2021-02-15 |  | 0
2 |  | 16-17 | KER-ALA-010 | Water Supply Sector- Augmentation & Modernization of Water Supply Distribution System in Alappuzha Municipality (Phase-II) | 2017-02-11 | 56.87 | Work divided in to 2 packages |  |  |  | 46.27
| 9 | 16-17 | ' | Pipe laying |  |  | Laying of 103 km pipes out of 126 km completed. Work started along Thathampally-Punnamada road & Dist. Court-Starting Point-Punnamada road | 87% | 2021-01-31 | Road Restoration charges remitted for PWD road Dist Court-Kaichoondi . But permission not granted from PWD. .
| 10 | 16-17 | ' | Setting up water kiosk |  |  | 1. Kiosk at Town hall construction completed. 2. Kiosk at Vaadakkal construction completed. 3. Kiosk at Thumboly construction completed. 4. Kiosk at Mangalam structural steel work ongoing. 5. Kiosk at Kaalath structural steel work ongoing. 6.Kiosk at Polabhagam- First step footing completed. 7 Kiosk at Aryad - Foundation work in progres 8.Kiosk at Thiruvambady -Foundation work in progres 9.Kiosk at Pazhaveedu site clearening completed and setting out the foundation trench . 10.Kiosk at Poomthoppu site clearening completed and setting out the foundation trench . 3 nos completed. 4 nos.Structural steelwork on going ,3 nos. foundation ongoing. | 55% | 2021-03-31
3 |  | 17-18 | KER-ALA-017 | Augmentation and modernization of water supply distribution system in Alappuzha Municipality (Phase-3) | 2017-02-11 | 58.13 | Work divided in to 2 packages |  |  |  | 46
| 11 | 17-18 | ' | Pipe laying |  |  | 133/191.5km completed. PWD road cutting permission obtained from PWD for 5 number of roads. Pipe laying work in progress . 5500 House connections completed. | 70% | 2021-03-31 | Road Restoration charges remitted for PWD road Dist Court-Kaichoondi . But permission not granted from PWD. .
| 12 | 17-18 | ' | Setting up water kiosk |  |  | 3nos. kiosks completed, 1no. structural steel work completed , 1no.structural steel work on going | 40% | 2021-03-31
|  |  |  | TOTAL |  | 148.9 |  |  |  |  | 107.143
KOCHI
PH DIVISION, KOCHI
WATER SUPPLY SECTOR
1 | 1 | 15-16 | KER-KOC-002 | Replacement of existing 525mm distribution cum pumping main with 600mm rider pumping main from Karuvelippady to Koovappadam in Kochi Corporation. | 23/2/2017 | 3.65 | Interconnection work at karuvelippady pump house and slab casting for concrete road is in progress. | 96% | 2021-02-03 |  | 2.3792
2 |  | 17-18 | KER-KOC-032 | Replacement of 5000 damaged Service water connections | 2017-02-11 | 5 | Work split in to 7 packages, Out of this, 4 packages executing by PH Division Kochi & 3 packages executing by JnNURM Division Kochi
| 2 | 17-18 |  | Karuvelippady Sub division (Domestic-950, Non Domestic-100) |  |  | Work completed | 100% | Completed
| 3 | 17-18 |  | Kaloor Sub Division (Domestic-300, Non Domestic-90) |  |  | Work in progress. Out of 390 Nos , 167 domestic and 18 Non domestic replaced | 47% | 2021-02-03
| 4 | 17-18 |  | Vyttila Sub Division (Domestic-600, Non Domestic-160) |  |  | Out of Domestic -600, 262 nos completed | 57% | 2021-03-30
| 5 | 17-18 |  | Pallimukku - W.W. Sub Division,Kochi - 16 (Domestic-750, Non Domestic-100) |  |  | 15% completed | 15% | 2021-03-30 |  | 0.02
|  |  |  | TOTAL |  | 5.65 |  |  |  |  | 2.3992
JnNURM DIVISION, KOCHI
WATER SUPPLY SECTOR
1 | 1 | 15-16 | KER-KOC-009 | Construction of 15L Ltrs. capacity GL tank at Karuvelippady in Kochi Corporation. | 23/2/2017 | 3.2 | Work completed on 31.5.2019 | 100% | Completed |  | 2.879
2 | 2 | 16-17 | KER-KOC-013 | Replacement of old 250mm CI pipe by 300mm DI K9 pipe along Konthuruthi road of Kochi Corporation. | 15/08/2017 & Revised AS on 1/1/2018 | 0.82 | Work completed on 8.3.2019 | 100% | Completed |  | 0.699
3 | 3 | 16-17 | KER-KOC-011 | Replacement of 100mm AC pipe by laying rider line of 160mm PVC CL 5 along both side at Pandit Karupan road of Kochi corporation. | 15/08/2017 & Revised AS on 04/01/2020 | 1.75 | Work completed on 30.5.2019 | 100% | Completed |  | 1.596
4 | 4 | 16-17 | KER-KOC-012 | Replacement of 100mm CI pipe by laying 160mm and 110mm PVC pipes from Valanjambalam to Ravipuram in Kochi corporation 2016-17. | 15/08/2017 | 0.66 | Work completed on 31.5.2019 | 100% | Completed |  | 0.675
5 | 5 | 16-17 | KER-KOC-017 | Laying of 450mm DI K9 pipe from north end of Aroor Edakochi bridge to KWA water tank site at Edakochi, Kochi corporation 2016-17. | 15/08/2017 & Revised AS on 04/01/2020 | 1.67 | Work completed on 25.3.2019 | 100% | Completed |  | 1.588
6 | 6 | 16-17 | KER-KOC-018 | Laying pumping main of 500mm DI pipe from JnNURM WTP at Maradu to Pumphouse at Thammanam for additional pumping of water (upto 18 MLD) to Kochi city in Kochi Corporation 2016-17. | 28/9/2017 | 16.5 | Pipe supply completed -5900 m. 2523 m laying completed Permission from NHAI pending. Joint inspection with NHAI and other utilities conducted on 22/1/21.NHAI asked kwa to get feasibility certificate from all utilities. Request sent to all utilities for the same. | 36% | 2021-05-31 | Sanction pending from NHAI and Railway | 12.88
7 | 7 | 16-17 | KER-KOC-019 | Laying rider main form Kathrikadavu to Elamkulam, Chettichira, Ponnurunni areas and distribution lines in Chakkaraparambu, Chalikkavattom areas 2016-17 | 1/1/2018 & Revised AS on 04/01/2020 | 3.65 | Completed | 100% | Completed |  | 3.217
8 | 8 | 16-17 | KER-KOC-015 | Construction of 17LL OHSR and 2.5 LL CWR at Pachalam. | 27/9/2017 | 7.75 | Pile cap PCC work completed for the half of sump portion and reinforcement work for pile cap is going on | 29% | 2021-07-30 |  | 2.43
9 | 9 | 16-17 | KER-KOC-020 | Construction of 15LL OHSR and 2LL CWR at Vadathode, Cheranalloor. | 27/9/2017 | 7.75 | Sump completed. OHSR Haunch concreting work is completed and reinforcement work of columns inside the tank is going on | 72% | 2021-07-30 |  | 2.222
10 | 10 | 16-17 | KER-KOC-021 | Construction of 10L Ltrs capacity OHSR at Thevara. | 27/9/2017 | 5.6 | Work completed on 24/9/2019 | 100% | Completed |  | 3.883
11 | 11 | 16-17 | KER-KOC-014 | Water supply sector - Kochi Corporation - Laying 500mm DI line from pumphouse at Thammanam to OHSR at Kadavanthara. | 2/11/2017 & Revised AS on 04/01/2020 | 7.76 | 500mm DI pipe laying completed. Trial run can be done after the railway crossing work at Ponnurunni is completed. | 99% | 2021-03-30 | Railway permission pending | 7.099
12 | 12 | 16-17 | KER-KOC-016 | Laying of 500mm transmission line from Karthikadavu to proposed Pachalam CWR | 2017-02-11 | 10.7 | Work in progress. 500 mm DI pipe - 3969 m laid | 87% | 2021-03-30 |  | 8.47
13 | 13 | 17-18 | KER-KOC-028 | Construction of 13 LL Capacity OHSR at Edakochi | 2017-02-11 | 6 | 600mm Pile -46/46 Nos completed. 500mm Pile 4/4 Nos completed. Reinforcement work of pile cap and plinth beam for 3 bays completed | 28% | 2021-07-01 |  | 1.588
14 | 14 | 17-18 | KER-KOC-029 | Construction of 25 LL OHSR at Karuvelippady | 2017-02-11 | 11.65 | Casting of 42 piles completed | 16% | 2021-11-03 |  | 0
15 | 15 | 17-18 | KER-KOC-030 | Construction of 40 LL OHSR at Kaloor | 2017-02-11 | 15 | Reinforcement work of haunch and side wall of sump in progress | 42% | 2021-09-30 |  | 6.86
16 | 16 | 17-18 | KER-KOC-031 | Laying 400 rnm DI K9 pipeline from Perumanoor to Ravipuram for a length of 1270m | 2/11/2017 | 4.4 | Pipe supplied completely & out of 1270 metre, 55m pipe laid. Due to presence of so many utilities existing in the highly traffic road, work couldnot continued. Since in the Hon: Mayor's meeting on 6/5/2019 a deviated route was proposed, which is also not feasible due to above condition. AS directed on 9/10/2020 by the Additional Chief Secretary the District collector has convened a meeting on 22/10/2020 with Worshipful Mayor, Corporation Authorities and KWA officials in presence of the Hon’ble MLA Sri. P.T.Thomas . Considering the space constraints due to the presence of number of existing pipes and cables in Old thevara road and MG road and difficulty in crossing MG road , KWA has suggested to use the existing 450mm CI pipe for 870m from Perumanoor pump house in the same alignment of 400mm DI pipe and to lay balance 400mm DI pipe for 400m to the existing OHSR at Ravipuram.As directed by the Worshipful Mayor .the District collector has instructed to test the 450mm CI pipe and to Check the stability of OHSR at Ravipuram. Provision for stability checking of OHSR is in the agreement of the work “Supplying and laying 400mm DI pipe from Perumanoor to Ravipuram.” Hence the contractor was directed to carry out the same through letters and over phone. But even after repeated instructions, the contractor has not carry out the work and has submitted a letter through mail on 27/11/2020 demanding rate enhancement for the work to be executed and price escalation for Cost of pipe which was already supplied. As the contractor has not taken up any action to carry out testing ,action is being taken to execute the testing of OHSR and 450mm CI pipe lines separately. | 26% | 2021-05-03 | As the contractor is not willing to restart the work ,the corporation is requested to preclose the work for rearranging the same. | 1.379
17 |  | 17-18 | KER-KOC-032 | Replacement of 5000 damaged Service water connections | 2017-02-11 | 5 | Work split in to 7 packages, Out of this, 4 packages executing by PH Division Kochi & 3 packages executing JnNURM Division Kochi |  |  |  | 0.229
| 17 | 17-18 |  | Shifting of existing water connections in Vennala-Janatha road, Arakkakadavu road and Subhash Chandra Bose road |  |  | Total connections shifted 315 nos | 100% | Completed
| 18 | 17-18 |  | Pandit Karuppan Road |  |  | 185 house connection and 12 Interconnections completed. Work completed on 22/8/2019 | 100% | Completed
| 19 | 17-18 |  | Valanjambalam- Ravipuram Road |  |  | 191 house connection & 3 interconnections completed .Work completed on 5/8/2019 | 100% | Completed
|  |  |  | TOTAL |  | 107.86 |  |  |  |  | 57.694
SEWERAGE SECTOR
1 | 1 | 15-16 | KER-KOC-010 | Rehabilitation of 5MLD STP plant at Elamkulam | 1/1/2018 & Revised AS on 25/01/2020 | 16.52 | Agreement executed on 31/12/2020. Site handing over note given to contractor dtd 31/12/2020. Functional drawings approved from CE(WASCON) and given to the contractor on 14.01.2021 Structural design submitted by the contractor on 22/01/2021 and approved by WASCON. Samples for mix design submitted to Engineering college. Site Clearing and survey work done. Equalisation tank setting out completed.Mobilization of equipments to site for piling of equilization tank completed.. | 1% | 2022-03-03 |  | 0
PH DIVISION THRISSUR | [10 empty] | 0
WATER SUPPLY SECTOR
1 | 1 | 15-16 | KER-THR-001 | Survey and Replacing of Faulty water meters and fixing new water meters at various service connections in Thrissur Corporation area. | 26/3/2016 | 3 | All works completed .except connection work. 330 nos connections given out of 500. | 85% | 2021-02-03 | Due to delay of getting documents for balance connections. | 1.326
2 | 2 | 15-16 | KER-THR-002 | Supply and installation of bulk flow water meters in transmission main and distribution system. | 26/3/2016 | 1 | Work completed on 27.06.2018 | 100% | Completed |  | 0.348
3 | 3 | 15-16 | KER-THR-003 | Supplying and laying 700mm DI K9 raw water gravity main from dam to aerator of 36 MLD WTP at Peechi. | 26/3/2016 | 1 | Work completed on 18.10.2018 | 100% | Completed |  | 0.925
4 | 4 | 15-16 | KER-THR-008 | Strengthening the exisiting distribution system to Thrissur Corporation area - Replacement of very old 80/100/125/300 AC and 700mm PREMO pipes with 110/140 PVC and 200/300/350mm DI pipes at varoius places in Thrissur Corporation . | 23/2/2017 | 14.4 | Work in progress | 94% | 2021-03-31 |  | 5.615
5 | 5 | 15-16 | KER-THR-009 | Renovation of existing damaged pump houses in Thrissur Corporation. | 23/2/2017 | 0.55 | Work completed | 100% | Completed |  | 0.348
6 | 6 | 15-16 | KER-THR-006 | Design, construction and commissioning of 3 MLD WTP, reservoir and pumping main for Ollukkara zone | 22/2/2018 | 6 | Land for WTP not received from Thrissur Corporation. In the meeting of ACS, LSGD conducted on 21/8/2019 decided to grant maximum 3 months time for finalizing the matter, otherwise the project will be cancelled. Since land not received yet, project may be dropped. |  |  | Thissur Corporation Authorities informed that they have identified 5 lands and isi n the process of arriving at fare value, so as to select the one with lowest value. The Mission Director, AMRUT informed that the Corporation has to finalize on any one piece of land since it will not be practical to get fair value for various piece of lands.The Chair of the meeting on 9.10.2020 directed the Corporation Secretary to finalize & inform which land is to be considered for the WTP. | 0
7 | 7 | 16-17 | KER-THR-016 | Replacement of very old 80/100/125/200/300 AC pipes with 160PVC and 200/300/mm Dl pipes at various places in Thrissur corporation | 2017-02-11 | 12.95 | 33 KMs out of 35 Kms completed. 94% completed. Demand note from PWD obtained for balance road. Work is progressing. | 94% | 2020-02-03 |  | 9.795
8 | 8 | 17-18 | KER-THR-028 | Laying of distribution lines from existing OHT at Kizhakumpattukara to Nellikunnu area for around 15 km with varying dia pipelines-(Dia 200 mm DI to 110 mm PVC | 13/11/2017 | 6 | Laying work in progress | 47% | 2021-03-31 |  | 1.694
9 | 9 | 17-18 | KER-THR-029 | Providing Dedicated Feeder from 33KV Pattikkad Sub station to Pumping Water Treatment Plant. | 2017-02-11 | 3 | KSEB dedicated feeder work completed. Transformer supplied Transformer room roof slab concrete completed | 8% | 2021-02-03 |  | 2.145
10 | 10 | 17-18 | KER-THR-033 | Floating intake structure at Peechi Reservoir | 2018-01-01 | 5 | Pump set with accessories supplied,100% pipe supplied,800 mm DI -302m laid out of 318m,700mmDI 56m laid out of 108m, Material of floating intake supplied, control panel board room completed, Floating intake structure assembly is in progress at Peechi Dam reservoir. Floating pontoon assembly completed.. | 60% | 2021-03-31 |  | 1.69
|  |  |  | TOTAL |  | 52.9 |  |  |  |  | 23.886
PROJECT DIVISION NATTIKA
THRISSUR
WATER SUPPLY SECTOR
1 | 1 | 15-16 | KER-THR-007 | Rehabilitation of Thrissur Corporation WSS to Koorkancherry Zone - Supply and laying seperate branched gravity main of 400mm DI K9 and replacement of 700mm PREMO with 700mm DI K9 pipe, and supply erection and commissioning of 65HP centrifugal motor pumpset for replacing of existing old pumpsets - 2nos at Koorkancherry sump allied works. | 23/2/2017 23/7/2020 (Revised A.S) | 3.71 | Work completed. Bill paid | 100% | Completed |  | 3.696
2 | 2 | 15-16 | KER-THR-005 | Completion of ongoing schemes - UWSS to Ollur and Edakkunni census town villages in Thrissur Corporation - Constriuction of 20L Ltrs capacity OHSR at Ollur and supplying , laying distribution lines and construction of retaining wall at WTP Arattupuzha. | 23/2/2017 | 11.4 | Laying of Distribution network 98% completed. WTP Compound wall not started.Solid block work 20LL OHSR started. | 95% | 2021-03-31 | Written permission for Edakkunni road- 500m along KIIFB road not obtained. As per the oral directions in the co-ordination meeting pipe line laid except in some reaches, some houses along KIIFB road are to be evacuated by PWD for completing the pipe laying work. Permission from Railway is to be obtained. An amount of 40000/- remitted to Divisional Railway Manager, Southern Railway TVM on 18.01.2020 vide DD No.681009 as centage charge. (1) Application ID & Date - SR-TVC-2019-30 dated 10.06.2019. (2) Location - Pudukkad and Ollur near Ollur over bridge ,Chainage - 40/300 & 40/400 | 11.52
3 | 3 | 16-17, 17-18 | KER- THR-015 & KER- THR-027 | Construction of new treatment plant of 20MLD WTP at Peechi | 28/9/2017 | 17.3 | All works are progressing simultaneously. Raw water pumping main, approach road formation and landscaping work started. All other finishing works tiles, electrical,mechanical, fabrication, painting are near completion. Approach road formation work in progress. | 85% | 2021-03-31 |  | 7.743
4 | 4 | 16-17 | KER-THR-017 | Zoning and mapping of water supply system of Thrissur Corporation- Supply and Laying of various dia pipes-Part-1 | 2018-01-01 | 8 | Work completed. | 100% | 2020-09-30 |  | 6.019
5 | 5 | 17-18 | KER-THR-026 | Zoning and mapping of water supply system of Thrissur Corporation- Supply and Laying of various dia pipes-Part-2 | 2018-01-01 | 17 | Out of 17.99Km,laying of distribution network 11.425 km completed. | 57% | 2021-03-31 |  | 10.237
6 | 6 | 17-18 | KER-THR-030 | Construction of 10LL OHSR at Anappara with pumping system and pumping main from Cherur to Anappara- Improvements of water supply system in Dn. 6, 7 and 8 of Thrissur Corporation- Part -1 | 2017-02-11 | 8 | Work Completed | 100% | Completed |  | 7.711
7 | 7 | 17-18 | KER-THR-031 | Supplying and laying distribution lines for Anappara Villadom area improvement of water Supply System in Dn.6,7 and 8 of Thrissur corporation- Part 2 | 2017-02-11 | 5.8 | Work Completed | 100% | Completed |  | 3.385
8 | 8 | 17-18 | KER-THR-032 | Construction of 5LL OHSR at Kuttanallur with gravity main and distribution network | 2017-02-11 | 8 | Laying of CWGM (20LL OHSR at Ollur to Kuttanellur Sump) 250mm DI K-9 Pipe - 3791.2 meter completed. Laying of Distribuition Network 5380.3meter completed. Construction of Valve chambers in progress. Construction of OHSR cum sump not started.. | 55% | 2021-07-31 | The cutting sanction received from PWD for the following roads only on 30.11.2020 1)Thalore–Thrissur road crossing (ch.7/250m)-280m, order dtd. 23.11.200 2)Thalore- Mannamangalam road (ch 3/700 to 4/100 )-400m, order dtd. 14.10.2020 But as per the oral directions in the co-ordination meeting pipe line laid along in the second road except in some reaches, some houses along KIIFB road are to be evacuated by PWD for completing the pipe laying work. | 4.605
|  |  |  | TOTAL |  | 79.21 |  |  |  |  | 54.916
GURUVAYUR
WATER SUPPLY SECTOR
1 | 1 | 15-16 | KER-GUR-001 | Improvements of coverage in Guruvayur Municipality - Laying distribution network for improvement of coverage in Guruvayur town area & Pookode zone. | 28/9/2017 & Revised AS on 25/05/2020 | 16.67 | Out of 41.17 Km, 37.885 Km pipe laid. Interconnection works completed.Valves with valve chamber completed- 22 Nos. Work partially commissioned. | 97% | 2021-03-31 |  | 10.11
2 | 2 | 16-17 | KER-GUR-007 | Construction of 10 LL OHSR and pumping main to Guruvayur, and balance distribution network to the Municipality. | 28/9/2017 & Revised AS on 25/05/2020 | 17.74 | Out of 9300 M, 2535 M pipe supplied and 400M laid. Sanctioned to terminate the original contract of the work with Sri.Paulose Abraham, following due procedures and to retender the balance work,complying the Judgment of the Hon'ble High Court of Kerala dated 15/12/2020 in WP(C) No : 26151 . Accordingy SE, Thrissur has terminated the contract. (Permission obtained for PWD road - Muthuvattur Guruvayur, in which CWPM is to be laid simultaneously with RWPM. The work is to be completed urgently within one month. Hence temporary arrangement for laying 500m 0f 400mm DI pipe in Muthuvattur Guruvayur road has been done. Ohsr tenndered with due date on 27.2.2021. 3.9 Kms of pipelaying work - tender notice ready. | 5% | 2021-07-31 |  | 1.142
3 |  | 16-17-18 |  | Improvement of water supply system for Guruvayur (Package II) | 28/9/2017 & Revised AS on 25/05/2020 | 81.34 | Work divided in to 2 packages
| 3 | 16-17 | KER-GUR-013 | Improvement of water supply system for Guruvayur (Package II) - Phase I |  | 11.65 | Work completed | 100% | Completed |  | 9.842
| 4 | 17-18 | KER-GUR-015 | Improvement of water supply system for Guruvayur (Package II) - Phase II |  | 69.69 | Out of 38.675Km, 21.41 km pipe laying completed. | 69% | 2021-03-04 | As per the Higher Level Committee in Government level, on 20.01.2021 a decision was taken to execute the Road Restoration works by Kerala Water Authority itself. Also for road cutting, sanction is needed from Legislative Assembly Coordination Committee. Matter has been placed before said committee, but no decision has been received yet. | 48.48
4 | 5 | 16-17 | KER-GUR-020 | Laying distribution networks in Thykkad zone - Guruvayur Municipality | 22/2/2018 & Revised AS on 25/05/2020 | 12.13 | 100% pipe supplied. Out of 20.958Km, 19.6 Km laying work completed. Valve chamber completed-5 Nos & Valve fitted -14 Nos | 93% | 2021-03-31 | PWD permission (1535m ) is to be obtained.(Common with RWPM). The amount not yet received from Municipal secretary Guruvayur and so not remitted in PWD till date. Permission from Railway authorities to be obtained for crossing railway line near Palayur Railway gate (LC No. 11) between chainages 20/0 and 20/100 Punkunnam (PNQ) and Guruvayoor (GVR) stations. Applied online on 8/11/2018. Application ID: SR-TVC-2018-88. Joint inspection conducted on 28/02/2019 and feasibility report with proposed sketch was submitted to TVM on 12/05/2019. P& E charges of Rs. 1,31,200/- paid on 09/08/2019. The location changed afterwards and joint inspection conducted and feasibility report submitted on 21/03/2020. | 8.603
5 | 6 | 17-18 | KER-GUR-014 | Construction of 10LL OHSR and Pumping Main to Guruvayur including distribution network(continuation project), Location: OHSR at Pookkode, pumping main and distribution at Municipal area. | 23/12/2017 & Revised AS on 25/05/2020 | 23 | 100% pipe supplied. Out of 53.689Km, 51.634 Km laying work completed. Shifting service connection out of 500 nos, 244 nos completed. Valves fitted- 84 Nos, Valve chamber completed- 10 Nos completed | 85% | 2021-03-31 | Road cutting permission is to be obtained from PWD for a length of 850m in Chavakkad Wadakkanchery road. | 12.757
|  |  |  | TOTAL |  | 150.88 |  |  |  |  | 90.934
PALAKKAD
WATER SUPPLY SECTOR
WS PROJECT DIVISION PALAKKAD
1 | 1 | 15-16 | KER-PAL-061 | Providing new pumping main 600mm DI-K9 - 3400m from Puthur Jn. to Moothanthara OHSR (Part-1) | 23/2/2017 | 5.44 | Work completed | 100% | Completed |  | 9.25
| 2 | 15-16 | KER-PAL-062 | Providing new pumping main 450mm DI-K9 - 4650m from Mattumantha to Kalmandapam. | 23/2/2017 | 4.56 | Work completed | 100% | Completed
2 | 3 | 16-17 | KER-PAL-052 | 600mm DI K9 New pumping main - From Malampuzha WTP to Mattumantha DI- K9 pipe 600 mm – 2850 m. | 15/08/2017 | 6.25 | Work has been completed. Trial run completed | 100% | Completed |  | 7.23
| 4 | 16-17 | KER-PAL-063 | Supply and errection of electromagnetic flow meter. | 15/08/2017 | 0.5 | Work completed | 100% | Completed
| 5 | 16-17 | KER-PAL-012 | Construction of 16L Ltrs OHSR at Kalmandapam KWA and demolishing the existing OHSR. | 15/08/2017 | 3 | Construction of OHSR Completed. Trial Run ongoing. | 100% | Completed
3 | 6 | 16-17 | KER-PAL-054 | Construction of 45 MLD water treatment plant at Malampuzha, KWA compound and booster station. | 28/09/2017 | 22.25 | Work in progress Filter House: Shuttering for side wall Clarifier 2: Shuttering for side wall first lift going on. | 45% | 2021-03-03 |  | 8.15
4 | 7 | 17-18 | KER-PAL-063 | Replacement of raw water and clear water pump set, transformers and electrification | 23/12/2017 | 1.44 | Pumps 55 KW 2 Nos Supplied | 20% | 2021-03-31 |  | 9.4422
| 8 | 17-18 | KER-PAL-064 | Constuction of OHSR 2 Nos , total 76.5LL capacity | 23/12/2017 | 11.56 | 37LL OHSR at Mattumantha - Vent cowls to be placed. 23.5 LL OHSR at Moothanthara - Structural work completed, Column pipe work finishing stage. Plastering in progress.Flow meters: 3 nos of 350mm and 1 no of 300mm Electro Magnetic flow meter supplied. | 90% | 2021-01-31
5 |  | 17-18 |  | Augmentation of Water Supply Scheme to Palakkad Mauncipality - Part III- Package II - Providing Rider main, changing of water connections and replacement of existing AC Pipelines to DI/PVC pipelines in Palakkad Muncipality. (Revised AS) | 23/12/2017 & Revised AS on 03/01/2020 | 85.15 | Work divided in to 3 packages
| 9 | 17-18 | KER-PAL-169 | Mattumantha Zone |  | 28.11 | 160mm PVC laying and AC Decommissioning work in progress . | 93% | 2021-02-03 |  | 12.5784
| 10 | 17-18 | KER-PAL-170 | Moothanthara Zone |  | 29.2087 | Linking and connection shifting works in progress. | 95% | 2021-02-03 |  | 11.9805
| 11 | 17-18 | KER-PAL-171 | Kalmandapam Zone |  | 27.8303 | Work in progress. Gap works completed. Linking and connection shifting works in progress. . | 97% | 2021-02-03 |  | 11.4341
|  |  |  | TOTAL |  | 140.15 |  |  |  |  | 70.0652
KOZHIKODE
WATER SUPPLY SECTOR
PH DIVISION KOZHIKODE
1 |  | 15-16 |  | Rehabilitation of old pipes, valves, interconnections with existing lines and providing water meters | 23/02/2017 | 17.87 | Work split in to 8 packages
| 1 | 15-16 | KER-KOZ-001 | Package 1 |  | 1.86 | Work completed | 100% | Completed |  | 0.806
| 2 | 15-16 | KER-KOZ-031 | Package 2 |  | 5.41 | Work completed | 100% | Completed |  | 4.408
| 3 | 15-16 | KER-KOZ-032 | Package 3 |  | 1.03 | Work completed | 100% | Completed |  | 0.654
| 4 | 15-16 | KER-KOZ-033 | Package 4 |  | 1.93 | Work completed | 100% | Completed |  | 1.964
| 5 | 15-16 | KER-KOZ-034 | Package 5 |  | 3.09 | Work completed | 100% | Completed |  | 3.795
| 6 | 15-16 | KER-KOZ-035 | Package 6 |  | 0.85 | Work completed | 100% | Completed |  | 0.636
| 7 | 15-16 | KER-KOZ-036 | Package 7 |  | 0.63 | Work completed | 100% | Completed |  | 0.099
| 8 | 15-16 | KER-KOZ-037 | Package 8 |  | 1.67 | Work completed | 100% | Completed |  | 0.514
|  | 16-17 |  | Rehabilitation of existing old pipes, valves and interconnection with the existing lines (Phase II) | 2/11/2017 & Revised AS on 12/05/2020 | 15.499 | Work split in to 7 packages
| 9 | 16-17 | KER-KOZ-005 | Package 1 |  | 1.1549 | Work completed | 100% | Completed |  | 1.153
| 10 | 16-17 | KER-KOZ-038 | Package 2 |  | 3.9849 | Work completed | 100% | Completed |  | 3.977
| 11 | 16-17 | KER-KOZ-039 | Package 3 |  | 1.9249 | Work completed | 100% | Completed |  | 1.915
| 12 | 16-17 | KER-KOZ-040 | Package 4 |  | 3.6249 | Work completed | 100% | Completed |  | 3.709
| 13 | 16-17 | KER-KOZ-041 | Package 5 |  | 3.4249 | Work completed | 100% | Completed |  | 3.421
| 14 | 16-17 | KER-KOZ-042 | Package 6 |  | 0.9849 | Work completed | 100% | Completed |  | 0.977
| 15 | 16-17 | KER-KOZ-043 | Package 7 |  | 0.3549 | Work completed | 100% | Completed |  | 0.345
3 |  | 16-17 |  | Strengthening of existing infrastructure facilities, and quality improvement of CWSS in Kozhikode Corporation | 2017-02-11 | 17.27 | Work split in to 3 packages |  |  |  | 7.17
| 16 | 16-17 | KER-KOZ-006 | Package 1 |  | 6.9 | 1450 m Laid out of 2100m. | 45% | 2021-03-30 | (1) 2.1km (Mini bypass mankav to kalluthankadavu) road cutting permission from PWD Proceedings from PWD recived on 25.11.2020. Action for executing agreement started. Work will start at the earliest. (2) 2600m (Malaparamba to Vellimadukunnu road) road cutting permission from NH not received. Request submitted to Executive Engineer,NH,Roads, Kozhikode on 12.06.2020 & 28.09.2020for getting road cutting permission.But demand notice not received till date
| 17 | 16-17 | KER-KOZ-044 | Package 2-Civil Works |  | 4 | Work completed | 100% | Completed
| 18 | 16-17 | KER-KOZ-049 | Package 3 - Electrical Works |  | 2.7 | Work in progress | 95% | 2021-02-03
|  |  |  | TOTAL |  | 50.639 |  |  |  |  | 35.543
PROJECT DIVISION KOZHIKODE
1 |  | 17-18 |  | Integrated Calicut Water Supply Project - phase 2 - Laying of distribution Lines in 10 zones | 2018-01-01 | 46.55 | Work split in to 10 packages |  |  |  | 29.54
| 1 | 17-18 | KER-KOZ-050 | Package 1-Balamandiram |  | 1.29 | Work completed | 100% | Completed
| 2 | 17-18 | KER-KOZ-051 | Package 2 - East hill zone |  | 5.03 | Pipe line laying and road reformation works in progress. | 94% | 2021-03-03
| 3 | 17-18 | KER-KOZ-052 | Package 3- Elathur zone |  | 1.6 | Work completed | 100% | Completed
| 4 | 17-18 | KER-KOZ-053 | Package 4-Eravathukunnu north one |  | 1.92 | Work completed | 100% | Completed
| 5 | 17-18 | KER-KOZ-046 | Package 5-Eravathukunnu south zone |  | 4.71 | Road Reformation work in preogress. | 99% | 2021-02-03
| 6 | 17-18 | KER-KOZ-054 | Package 6-Malaparamba zone |  | 5.17 | Pipe line laying and road reformation works in progress. | 93% | 2021-03-03
| 7 | 17-18 | KER-KOZ-045 | Package 7-Pottammel zone |  | 6.8 | Work completed | 100% | Completed
| 8 | 17-18 | KER-KOZ-048 | Package 8-Cheruvannur zone |  | 2.74 | Work completed | 100% | Completed
| 9 | 17-18 | KER-KOZ-047 | Package 9-Kovoor zone |  | 6.51 | Work completed | 100% | Completed
| 10 | 17-18 | KER-KOZ-015 | Package 10-Beypur zone |  | 10.67 | Work completed | 100% | Completed
|  |  |  | TOTAL |  | 46.55 |  |  |  |  | 29.54
KANNUR
WATER SUPPLY SECTOR
PROJECT DIVISION KANNUR
1 | 1 | 15-16 | KER-KAN-003 | Laying Gravity Main from JICA project at Mangattuparamba to Pallikunnu OHSR for Pallikkunnu & Puzhathi Villages. | 23/2/2017 | 23.5 | Work completed on 21/01/2020 and commissioned | 100% | Completed |  | 19.747
2 | 2 | 15-16 | KER-KAN-002 | Construction of 24LL OHSR at Pallikkunnu for Pallikkunnu & Puzhathi Villages. | 23/2/2017 | 4.05 | Work Completed and commissioned on 03.05.2020 | 100% | Completed |  | 4.286
3 | 3 | 15-16 | KER-KAN-025 | Construction of 14LL capacity OHSR Thottada at Edakkad zone III in Kannur Corporation. | 15/08/2017 | 3 | Work completed, commissioned on 08.02.2020 | 100% | Completed |  | 3.161
4 | 4 | 15-16 | KER-KAN-001 | Rehabilitation of old distribution networks, valves, house service connections and inter-connections in Kannur Corporation SAAP 2015-16 - (Puzhathi) | 28/9/2017 & Revised AS on 16/12/2019 | 17.7 | Work Completed | 100% | Completed |  | 16.079
5 | 5 | 16-17 | KER-KAN-008 | Rehabilitation of existing old distribution network, valves, house service connection and inter-connections with existing lines and providing flow meters etc., including road reformation charges-Phase II at Pallikkunnu. | 28/9/2017 & Revised AS on 16/12/2019 | 15.62 | Work completed | 100% | Completed |  | 12.492
6 | 6 | 16-17 | KER-KAN-006 | Laying of gravity main from water supply system to Kannur at Melechowa to sump at Avera to OHSR at Thottada including erection of pumpsets at Avera in Kannur Corporation 2016-17 | 15/08/2017 | 6.8 | Work completed except railway crossing.Trial run completed with temporary arrangement, Regualr water supply started. | 98% | 2021-02-02 |  | 6.366
7 | 7 | 16-17 | KER-KAN-007 | Enhancing capacity of treatment plant from 30 MLD to 40 MLD including modernisation of existing treatment plant. | 2017-02-11 | 7.8 | Completed on 31/10/2020 Under trial run | 100% | Completed |  | 6.43
8 | 8 | 17-18 | KER-KAN-016 | Supplying and Laying new distribution lines in Pallikkunnu and Puzhathi area providing new service connection and inter connection with existing lines. | 2/11/2017 & Revised AS on 16/12/2019 | 4.25 | Work Completed | 100% | Completed |  | 3.356
9 | 9 | 17-18 | KER-KAN-026 | Laying new distribution line and providing new service connection at Elayavoor zone | 23/12/2017 & Revised AS on 16/12/2019 | 8.36 | Work Completed | 100% | Completed |  | 6.82
10 | 10 | 17-18 | KER-KAN-027 | Laying new distribution line 385km and providing new service connection at Edakkad zone | 23/12/2017 & Revised AS on 16/12/2019 | 5.79 | Laying completed (10.02 Km), except railway crossing. Oral permission obtained but caution date not confirmed by Railway. | 98% | 2021-02-03 | Rail crossing- 743/400-743/300-Permission granted.Sanction awaited Again submitted the request for caution of railway crossing on 8.1.2021 Oral permission obtained but caution date not confirmed by Railway. | 6.163
11 | 11 | 17-18 | KER-KAN-015 | Rehabilitation of existing old distribution network, valves, house service connection and inter-connections with existing lines and providing flow meters etc., including road reformation charges (PWD/ NH/ Corporation)at Elayavoor zone | 23/12/2017 & Revised AS on 16/12/2019 | 11.57 | Work completed | 100% | Completed |  | 10.254
12 | 12 | 17-18 | KER-KAN-024 | Rehabilitation of existing old distribution network, valves, house service connection and inter-connections with existing lines and providing flow meters etc., including road reformation charges (PWD/ NH/ Corporation)at Edakkad zone | 23/12/2017 & Revised AS on 16/12/2019 | 8.95 | Work completed | 100% | Completed |  | 8.77
|  |  |  | TOTAL |  | 117.39 |  |  |  |  | 103.924